## Final Checklist - UK Expansion
Checklist Area | Checklist item | Who owns it | When | Why it matters | Evidence / output | Risks if missed
Company setup | Decide whether to incorporate a UK private limited company | Founder / Legal | Pre-UK entry | Incorporation affects how you contract, hire, pay tax and engage with UK customers. | Operating model decision memo referencing chosen structure | Misaligned operating model leading to delays in contracting or hiring
Company setup | Plan incorporation steps and required company details | Legal / Ops | Pre-UK entry | Clear planning avoids errors or delays during registration and early operations. | Incorporation plan (actions, roles, required information) | Incorporation delays and incomplete filings
Company setup | Incorporate the UK company (if chosen) | Legal / Ops | Month 0–1 | Incorporation creates the UK entity needed for payroll, contracts and tax registration. | Certificate of incorporation and company number | Unable to proceed with UK operations as planned
Company setup | Establish a filing and governance cadence (accounts, confirmations, directors) | Legal / Ops | Month 1–3 | Ongoing compliance is required to maintain good standing with Companies House. | Compliance calendar and responsibilities matrix | Missed filings and avoidable compliance issues
Companies House compliance | Create an ECCT identity verification plan for directors and PSCs (ahead of rollout) | Legal | Pre-UK entry / Month 0–1 | Identity verification will become mandatory and may delay filings or appointments if unprepared. | ID verification plan aligned with Companies House timelines | Filings or appointments blocked due to verification issues
Employment & people | Register as an employer with HMRC (PAYE) | Finance / Ops | Month 0–1 | PAYE registration is legally required before the first payday. | PAYE registration confirmation | Illegal payroll operation and penalties
Employment & people | Put right-to-work check process in place | Ops / HR | Month 0–1 | Proper checks provide a statutory excuse against civil penalties. | Documented RTW process and completed checks | Fines or enforcement action
Immigration | Assess whether sponsorship will be required for founders or hires | Founder / HR | Pre-UK entry | Sponsorship requirements affect role design, salary thresholds and hiring feasibility. | Immigration assessment note | Inability to hire planned roles
Immigration | Apply for a Sponsor Licence (if required) | Legal / HR | Month 0–1 | A licence is mandatory before sponsoring most non-UK workers. | Sponsor licence application and approval | Delayed or blocked overseas hiring
Immigration | Design roles and salary levels in line with visa rules | Founder / HR | Month 1–3 | Visa criteria directly shape job scope and compensation. | Role descriptions aligned with visa requirements | Non-compliant job offers
Immigration | Recruit and onboard sponsored workers | HR | Month 1–3 | Hiring can only proceed lawfully once sponsorship is in place. | Employment contracts and visa records | Hiring delays or visa refusals
Tax & finance | Register for Corporation Tax and set reporting calendar | Finance | Month 0–1 | Corporation Tax obligations apply from incorporation. | HMRC registration and tax calendar | Missed filings and penalties
Tax & finance | Assess VAT exposure (including NETP rules for cross-border SaaS) | Finance / Tax | Pre-UK entry | Non-Established Taxable Person rules may require VAT registration even without a UK office. | VAT assessment memo | Unexpected VAT liabilities
Tax & finance | Register for VAT if required | Finance | Month 0–1 | VAT registration ensures lawful charging and recovery of VAT. | VAT registration certificate | Non-compliant invoicing
Tax & finance | Assess eligibility for R&D tax relief or ERIS | Finance / Advisor | Month 1–3 | Reliefs can materially affect cash flow and funding runway. | R&D eligibility assessment | Missed tax relief opportunities
Data & trust | Define controller / processor role under UK GDPR | Legal / Data | Month 0–1 | Legal responsibilities differ significantly depending on role. | Data role classification document | Misallocated liability
Data & trust | Put UK GDPR-compliant privacy notices and records in place | Legal / Data | Month 0–1 | Transparency is a core legal requirement and buyer expectation. | Published privacy notice and RoPA | Regulatory scrutiny
Data & trust | Implement international data transfer safeguards (IDTA or UK Addendum, if data leaves the UK) | Legal / Data | Month 1–3 | Safeguards are required for lawful cross-border data transfers. | Signed IDTA or UK Addendum | Unlawful data transfers
Data & trust | Conduct a DPIA where processing is high-risk | Legal / Data | Month 1–3 | DPIAs help identify and mitigate data protection risks. | Completed DPIA | Increased regulatory risk
Cyber security | Assess Cyber Essentials requirement for target customers | Ops / Security | Month 1–3 | Certification is often expected in public-sector procurement. | Gap assessment | Blocked procurement routes
Built environment | Map devolved planning regimes relevant to your product | Product / Sales | Pre-UK entry | Planning workflows differ across UK nations and affect integrations. | Market and product mapping | Late-stage integration friction
Public sector sales | Identify relevant public-sector procurement routes (e.g. frameworks) | Sales / Ops | Month 1–3 | Understanding routes to market avoids wasted sales effort. | Procurement route assessment | Missed or delayed opportunities
Ongoing compliance | Monitor Companies House, HMRC and ICO regulatory updates (recurring / annual) | Legal / Ops | Ongoing | UK regulatory frameworks continue to evolve. | Update log or review schedule | Falling out of compliance over time
Ongoing compliance | Review data protection and security posture regularly (recurring / annual) | Legal / Security | Ongoing | Ongoing review maintains trust and compliance as guidance changes. | Annual review notes | Increased regulatory or commercial risk
This guide has been produced by the UK PropTech Association, provided for general guidance and educational purposes only. Founders should seek professional advice and consult with official sources.